|  |  |  |  |
| --- | --- | --- | --- |
| Task code | Task description | Immediately preceding tasks | Task duration, days |
| A | Acquisition of graphics processor | - | 7 |
| B | Neural network framework programming | A | 28 |
| C | Procurement of testing materials | - | 14 |
| D | Determination of sampling techniques | C | 6 |
| E | Random sampling of chords | D | 1 |
| F | Neural network training, testing & data collection | B, E | 42 |
| G | Data analysis | F | 7 |